## MASTER_TC
TC ID | Hari | Modul | Fitur | Jenis Uji | Prioritas | Prasyarat | Langkah Uji | Expected Result | Actual Result | Status | Severity | Bug ID | Bukti | Penguji | Tanggal Uji | Commit/Build | Catatan
TC-API-001 |  | API | GET List Assets | Normal | P1 | Backend jalan, Postman siap | 1. Buka Postman 2. Kirim GET /api/assets 3. Amati response | HTTP 200, list aset tampil | [5 empty] | Reza Tri |  |  | Test pertama — BLOCKED karena backend belum jalan
TC-API-002 | 8 | API | GET Detail Asset | Normal | P1 |  |  | HTTP 200, detail aset tampil | [5 empty] | Reza Tri
TC-API-003 | 8 | API | POST Create Asset | Normal | P1 |  |  | HTTP 201, aset tersimpan | [5 empty] | Reza Tri
TC-API-004 | 8 | API | POST tanpa field wajib | Negatif | P1 |  |  | HTTP 400, error jelas | [5 empty] | Reza Tri
TC-API-005 | 8 | API | GET ID tidak ada | Negatif | P1 |  |  | HTTP 404, error jelas | [5 empty] | Reza Tri
TC-API-006 | 9 | API | PUT Update Asset | Normal | P1 |  |  | HTTP 200, data terupdate | [5 empty] | Reza Tri
TC-API-007 | 9 | API | DELETE Asset | Normal | P1 |  |  | HTTP 200, aset terhapus | [5 empty] | Reza Tri
TC-API-008 | 9 | API | Validasi IP Address | Boundary | P2 |  |  | HTTP 400, error jelas | [5 empty] | Reza Tri
TC-API-009 | 9 | API | Duplikasi Asset Code | Negatif | P1 |  |  | HTTP 409, error duplicate | [5 empty] | Reza Tri
TC-API-010 | 9 | API | Endpoint tanpa auth | Negatif | P1 |  |  | HTTP 401 Unauthorized | [5 empty] | Reza Tri
TC-API-011 | 10 | API | Response time < 2 detik | Boundary | P2 |  |  | Response time < 2000 ms | [5 empty] | Reza Tri
TC-ASSET-001 | 13 | Assets | Verifikasi aset Router MikroTik RB4011 terdaftar | Normal | P1 | Bearer token, aset terdaftar | 1. GET /assets 2. Cari asset_code NET-RTR-01 3. Cek field lengkap | 200, data: asset_code, asset_name, category Router, ip_address, monitoring_method Ping |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-002 | 13 | Assets | Verifikasi aset Switch Cisco 2960 terdaftar | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code NET-SWD-01 3. Cek detail | 200, category Switch Manageable, monitoring_method Ping/SNMP |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-003 | 13 | Assets | Verifikasi aset Access Point UniFi U6-Lite | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code NET-AP-01 3. Cek detail | 200, category Access Point, monitoring_method Ping/SNMP |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-004 | 13 | Assets | Verifikasi aset Server T-AIMS Ubuntu | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code SRV-TAIMS-01 3. Cek detail | 200, category Server, monitoring_method HTTP |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-005 | 13 | Assets | Verifikasi aset Firewall pfSense | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code NET-FW-01 3. Cek detail | 200, category Firewall, monitoring_method Ping |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-006 | 13 | Assets | Verifikasi aset Storage Synology DS220+ | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code STO-NAS-01 3. Cek detail | 200, category Storage, monitoring_method Ping |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-007 | 13 | Assets | Verifikasi aset IoT Node ESP32 | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code IOT-ESP-01 3. Cek detail | 200, category IoT Node, monitoring_method Heartbeat, monitoring_config mqtt_topic |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-008 | 13 | Assets | Verifikasi aset CCTV Head Office | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code SEC-CCTV-01 3. Cek detail | 200, category CCTV, monitoring_method Ping + HTTP |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-009 | 13 | Assets | Verifikasi aset PC Head Office 01 | Normal | P1 | Bearer token | 1. GET /assets 2. Cari asset_code PC-HO-01 3. Cek detail | 200, category PC, monitoring_method Ping |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-010 | 13 | Assets | Filter by category Router | Normal | P1 | Bearer token | 1. GET /assets?category=Router 2. Cek hasil | 200, hanya Router yang tampil |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-011 | 13 | Assets | Filter by category IoT Node | Normal | P1 | Bearer token | 1. GET /assets?category=IoT Node 2. Cek hasil | 200, hanya IoT Node (ESP32, RPi) tampil |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-012 | 13 | Assets | Filter by location Head Office | Normal | P2 | Bearer token | 1. GET /assets?location_id=2 2. Cek hasil | 200, hanya aset di Head Office |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-013 | 13 | Assets | Verifikasi IP MikroTik 192.168.10.1 | Normal | P1 | Bearer token | 1. GET /assets/NET-RTR-01 2. Cek field ip_address | 200, ip_address = 192.168.10.1 |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-014 | 13 | Assets | Verifikasi monitoring_config ESP32 mqtt_topic | Normal | P1 | Bearer token | 1. GET /assets/IOT-ESP-01 2. Cek monitoring_config.mqtt_topic | 200, mqtt_topic = taims/heartbeat/IOT-ESP-01 |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-ASSET-015 | 13 | Assets | Verifikasi priority aset kritis = 1 | Normal | P2 | Bearer token | 1. GET /assets?priority=1 2. Cek hasil | 200, semua aset priority 1 tampil |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-INC-001 | 27 | Incidents | Simulasi KABEL PUTUS - Switch Cisco | Failure | P1 | Kabel uplink siap dicabut | 1. Catat status awal switch 2. Cabut kabel LAN uplink 3. Tunggu threshold 4. Cek status di API | Status berubah offline, incident tercatat, notifikasi terkirim |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-002 | 27 | Incidents | Simulasi KABEL PUTUS - Recovery | Failure | P1 | Kabel siap dicolok kembali | 1. Sambung kabel LAN 2. Tunggu heartbeat 3. Cek status | Status kembali online, incident resolved, recovery alert terkirim |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-003 | 27 | Incidents | Simulasi KABEL PUTUS - Router MikroTik | Failure | P1 | Kabel WAN siap dicabut | 1. Catat status 2. Cabut kabel WAN 3. Cek monitoring | Status offline, incident type "Connection Loss", severity high |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-004 | 27 | Incidents | Simulasi POWER CUT - Raspberry Pi | Failure | P1 | RPi terpasang adaptor | 1. Cabut adaptor power RPi 2. Tunggu 90 detik 3. Cek API status | Status offline, last_seen stop, heartbeat berhenti |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-005 | 27 | Incidents | Simulasi POWER CUT - ESP32 | Failure | P1 | ESP32 terpasang USB | 1. Cabut USB power ESP32 2. Tunggu 90 detik 3. Cek API | Status offline, LWT MQTT trigger offline |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-006 | 27 | Incidents | Simulasi POWER CUT - Server T-AIMS | Failure | P1 | Server bisa di-restart | 1. Matikan server 2. Cek dari laptop lain 3. Cek HTTP health check | HTTP check gagal, status offline, incident critical |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-007 | 27 | Incidents | Simulasi POWER CUT - Recovery ESP32 | Failure | P1 | ESP32 siap dinyalakan | 1. Nyalakan ESP32 2. Tunggu heartbeat kirim 3. Cek status | Status online, recovery alert terkirim, last_seen update |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-008 | 27 | Incidents | Verifikasi incident tercatat di database | Normal | P1 | Ada incident dari simulasi | 1. GET /incidents?status=open 2. Cek field | 200, incident dengan detected_at, severity, incident_status |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-009 | 27 | Incidents | Update incident status resolved | Normal | P1 | Ada incident open | 1. PUT /incidents/:id 2. Body status=resolved 3. Cek response | 200, incident_status = resolved |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-010 | 27 | Incidents | Notifikasi offline terkirim saat kabel putus | Failure | P1 | MQTT & Telegram aktif | 1. Cabut kabel 2. Cek Telegram/Email | Alert diterima dalam 90 detik, isi device_code + waktu |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-011 | 27 | Incidents | Notifikasi recovery terkirim | Failure | P1 | MQTT & Telegram aktif | 1. Sambung kabel 2. Cek Telegram | Recovery alert terkirim setelah status online |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-INC-012 | 27 | Incidents | Tidak ada duplikasi alert saat flapping | Failure | P2 | Cooldown 5 menit | 1. Cabut-nyambung kabel 3x dalam 2 menit 2. Cek Telegram | Hanya 1 alert offline + 1 alert recovery |  | PASS |  |  |  | Reza Tri | 27/10/2026
TC-AUTH-001 | 8 | Auth | Login sukses dengan kredensial valid | Normal | P1 | Contract API v0.5 | 1. POST /auth/login 2. Body valid 3. Amati response | 200 OK, token + user data |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-AUTH-002 | 8 | Auth | Login gagal - password salah | Negatif | P1 | Contract API v0.5 | 1. POST /auth/login 2. Password salah 3. Amati | 401, error password salah |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-AUTH-003 | 8 | Auth | Login tanpa email/password | Negatif | P1 | Contract API v0.5 | 1. POST /auth/login 2. Body kosong 3. Amati | 400, error wajib diisi |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-AUTH-004 | 8 | Auth | GET /auth/me dengan token valid | Normal | P1 | Login dulu | 1. GET /auth/me 2. Bearer token 3. Amati | 200, data user login |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-AUTH-005 | 8 | Auth | GET /auth/me tanpa token | Negatif | P1 | - | 1. GET /auth/me 2. Tanpa auth 3. Amati | 401 Unauthorized |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-AUTH-006 | 8 | Auth | Change password berhasil | Normal | P2 | Login dulu | 1. POST /auth/change-password 2. Body old+new 3. Amati | 200, password berubah |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-USER-001 | 9 | Users | GET /users sebagai admin | Normal | P1 | Bearer admin | 1. GET /users 2. Amati response | 200, list user |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-USER-002 | 9 | Users | GET /users sebagai user (403) | Negatif | P1 | Bearer user | 1. GET /users 2. Amati response | 403 Forbidden |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-USER-003 | 9 | Users | POST create user | Normal | P1 | Bearer admin | 1. POST /users 2. Body valid 3. Amati | 201, user_id baru |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-USER-004 | 9 | Users | POST email duplikat (409) | Negatif | P1 | Bearer admin | 1. POST /users 2. Email sudah ada 3. Amati | 409 Conflict |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-USER-005 | 9 | Users | DELETE user sebagai admin (403) | Negatif | P1 | Bearer admin | 1. DELETE /users/:id 2. Amati | 403 Forbidden |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-LOC-001 | 10 | Locations | GET list lokasi | Normal | P1 | Bearer token | 1. GET /locations 2. Amati | 200, 2 lokasi (HO, Marketing) |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-LOC-002 | 10 | Locations | POST create lokasi | Normal | P2 | Bearer admin | 1. POST /locations 2. Body valid 3. Amati | 201 Created |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-LOC-003 | 10 | Locations | DELETE lokasi dipakai (409) | Negatif | P2 | Bearer super_admin | 1. DELETE /locations/:id (ada aset) 2. Amati | 409 Conflict |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MON-001 | 11 | Monitoring | POST /monitoring/ping | Normal | P1 | Ananda engine | 1. POST /monitoring/ping 2. Body valid 3. Amati | 201, log_id |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MON-002 | 11 | Monitoring | POST /monitoring/http | Normal | P1 | Ananda engine | 1. POST /monitoring/http 2. Body valid 3. Amati | 201, log_id |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MON-003 | 11 | Monitoring | POST /monitoring/tcp | Normal | P1 | Ananda engine | 1. POST /monitoring/tcp 2. Body valid 3. Amati | 201, log_id |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MON-004 | 11 | Monitoring | GET monitoring logs | Normal | P1 | Bearer token | 1. GET /monitoring/logs 2. Amati | 200, list log |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MON-005 | 11 | Monitoring | GET monitoring summary | Normal | P1 | Bearer token | 1. GET /monitoring/summary 2. Amati | 200, ringkasan status |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-HB-001 | 13 | Heartbeat | POST heartbeat valid | Normal | P1 | Device terdaftar | 1. POST /heartbeat 2. Body valid 3. Amati | 200, next_heartbeat_in |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-HB-002 | 13 | Heartbeat | POST device_id tidak terdaftar | Negatif | P1 | - | 1. POST /heartbeat 2. device_id salah 3. Amati | 404, error device_id tidak terdaftar |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-HB-003 | 13 | Heartbeat | GET heartbeat terakhir | Normal | P2 | Bearer token | 1. GET /heartbeat/:assetCode/latest 2. Amati | 200, data heartbeat |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MNT-001 | 17 | Maintenance | GET list maintenance | Normal | P2 | Bearer token | 1. GET /maintenance 2. Amati | 200, list maintenance |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-MNT-002 | 17 | Maintenance | POST create maintenance | Normal | P2 | Bearer admin | 1. POST /maintenance 2. Body valid 3. Amati | 201, maintenance_id |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-NOTIF-001 | 21 | Notifications | GET list notifikasi | Normal | P1 | Bearer token | 1. GET /notifications 2. Amati | 200, list notifikasi |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-NOTIF-002 | 21 | Notifications | PUT mark as read | Normal | P2 | Bearer token | 1. PUT /notifications/:id/read 2. Amati | 200, is_read=true |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-NOTIF-003 | 21 | Notifications | POST create notifikasi | Normal | P2 | Bearer admin | 1. POST /notifications 2. Body valid 3. Amati | 201, notification_id |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-DASH-001 | 15 | Dashboard | GET dashboard stats | Normal | P1 | Bearer token | 1. GET /dashboard/stats 2. Amati | 200, total/online/offline |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-DASH-002 | 19 | Dashboard | GET dashboard uptime | Normal | P1 | Bearer token | 1. GET /dashboard/uptime 2. Amati | 200, uptime per device |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-DASH-003 | 19 | Dashboard | GET dashboard top-issues | Normal | P2 | Bearer token | 1. GET /dashboard/top-issues 2. Amati | 200, device bermasalah |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-DASH-004 | 15 | Dashboard | GET dashboard charts | Normal | P1 | Bearer token | 1. GET /dashboard/charts 2. Amati | 200, data grafik |  | PASS |  |  |  | Reza Tri | 2026-12-10
TC-DASH-005 | 24 | Dashboard | GET dashboard AI report | Normal | P2 | Bearer token | 1. GET /dashboard/ai-report 2. Amati | 200, summary + recommendation |  | PASS |  |  |  | Reza Tri | 2026-12-10

## BUG_REPORTS
Bug ID | Judul | Dilaporkan oleh | Tanggal | Modul | Severity | Priority | Environment | Commit/Build | Langkah Reproduksi | Expected Result | Actual Result | Frekuensi | Dampak | Bukti | Status | PIC Perbaikan | Verified oleh | Tanggal Verifikasi | Catatan Verifikasi
BUG-001 | Status device tetap Online padahal ESP32 mati | Reza Tri | 2026-11-10 | Monitoring | Critical | P1 | Staging | abc1234 | 1. ESP32 online 2. Matikan 3. Tunggu 6 menit 4. Refresh dashboard | Status Offline | Status masih Online | Selalu | Monitoring tidak akurat | screenshots/BUG-001.png | Open | Ananda |  |  |  | Menunggu perbaikan
BUG-002 | Endpoint PUT 500 Internal Server Error | Reza Tri | 2026-11-10 | API | High | P1 | Staging | abc1234 | 1. PUT /api/assets/AST-001 2. Body valid 3. Amati response | HTTP 200, data terupdate | HTTP 500 | Selalu | Update aset tidak bisa | screenshots/BUG-002.png | Open | Ahmad Reza |  |  |  | Menunggu fix

## EXECUTION_LOG
Tanggal | Hari ke- | Shift | Total TC | PASS | FAIL | BLOCKED | SKIP | Bug Baru | Bug Verified | Catatan | Link Test Report
2026-11-10 | 1 | Shift 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Setup QA & Docs, blocker backend | test-reports/2026-10-11_Hari-1.md
2026-12-10 | 2 | Shift 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Susun test case tambahan | test-reports/2026-10-12_Hari-2.md
13/10/2026 | 3 | Shift 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Validasi test case dengan Damar | test-reports/2026-10-13_Hari-3.md
14/10/2026 | 4 | Shift 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review acceptance criteria | test-reports/2026-10-14_Hari-4.md
15/10/2026 | 5 | Shift 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review architecture | test-reports/2026-10-15_Hari-5.md
16/10/2026 | 6 | Shift 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Uji schema database | test-reports/2026-10-16_Hari-6.md
17/10/2026 | 7 | Shift 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Test checklist wireframe | test-reports/2026-10-17_Hari-7.md
18/10/2026 | 8 | Shift 2 | 5 | 4 | 1 | 0 | 0 | 1 | 0 | API dasar + smoke test | test-reports/2026-10-18_Hari-8.md
19/10/2026 | 9 | Shift 2 | 5 | 4 | 1 | 0 | 0 | 1 | 1 | API validation | test-reports/2026-10-19_Hari-9.md
20/10/2026 | 10 | Shift 2 | 4 | 3 | 1 | 0 | 0 | 1 | 0 | Smoke test MVP | test-reports/2026-10-20_Hari-10.md
21/10/2026 | 11 | Shift 2 | 6 | 5 | 1 | 0 | 0 | 1 | 0 | Monitoring engine | test-reports/2026-10-21_Hari-11.md
22/10/2026 | 12 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Retry logic | test-reports/2026-10-22_Hari-12.md
23/10/2026 | 13 | Shift 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Heartbeat normal | test-reports/2026-10-23_Hari-13.md
24/10/2026 | 14 | Shift 2 | 5 | 4 | 1 | 0 | 0 | 1 | 0 | Reconnect test | test-reports/2026-10-24_Hari-14.md
25/10/2026 | 15 | Shift 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Dashboard utama | test-reports/2026-10-25_Hari-15.md
26/10/2026 | 16 | Shift 2 | 5 | 4 | 1 | 0 | 0 | 1 | 0 | List & filter | test-reports/2026-10-26_Hari-16.md
27/10/2026 | 17 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Detail device | test-reports/2026-10-27_Hari-17.md
28/10/2026 | 18 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | History | test-reports/2026-10-28_Hari-18.md
29/10/2026 | 19 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Uptime/downtime | test-reports/2026-10-29_Hari-19.md
30/10/2026 | 20 | Shift 2 | 6 | 5 | 1 | 0 | 0 | 1 | 0 | MVP release | test-reports/2026-10-30_Hari-20.md
31/10/2026 | 21 | Shift 2 | 4 | 3 | 0 | 1 | 0 | 1 | 0 | Offline alert | test-reports/2026-10-31_Hari-21.md
2026-01-11 | 22 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Recovery alert | test-reports/2026-11-01_Hari-22.md
2026-02-11 | 23 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Map/location | test-reports/2026-11-02_Hari-23.md
2026-03-11 | 24 | Shift 2 | 5 | 4 | 0 | 1 | 0 | 0 | 0 | AI automation | test-reports/2026-11-03_Hari-24.md
2026-04-11 | 25 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Reporting | test-reports/2026-11-04_Hari-25.md
2026-05-11 | 26 | Shift 2 | 9 | 7 | 2 | 0 | 0 | 2 | 1 | Security test | test-reports/2026-11-05_Hari-26.md
2026-06-11 | 27 | Shift 2 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Failure simulation | test-reports/2026-11-06_Hari-27.md
2026-07-11 | 28 | Shift 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Regression test | test-reports/2026-11-07_Hari-28.md
2026-08-11 | 29 | Shift 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | Dokumentasi | test-reports/2026-11-08_Hari-29.md
2026-09-11 | 30 | Shift 2 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Final demo | test-reports/2026-11-09_Hari-30.md

## DASHBOARD
Modul | Total TC | PASS | FAIL | BLOCKED | % Progress
API | 11 | 0 | 0 | 0 | 0%
Device Monitoring | 0 | 0 | 0 | 0 | 0
Last Seen | 0 | 0 | 0 | 0 | 0
Response Time | 0 | 0 | 0 | 0 | 0
Monitoring History | 0 | 0 | 0 | 0 | 0
Uptime / Downtime | 0 | 0 | 0 | 0 | 0
Dashboard | 5 | 5 | 0 | 0 | 1
Location | 0 | 0 | 0 | 0 | 0
Notification | 0 | 0 | 0 | 0 | 0
User Management | 0 | 0 | 0 | 0 | 0
Reporting | 0 | 0 | 0 | 0 | 0
AI Automation | 0 | 0 | 0 | 0 | 0